## Info
Magnet Strength Limits
This workbook summarizes grandient strength limits for magnet types used in MAX 4U |  |  |  | Brho | 10.0086 | T.m
Note: Multipole definitions include the factorial in the Taylor expansion, i.e.
Revision History |  |  |  | Sextupole Gradient = 1/2*d2B/dx2, Octupole Gradient = 1/6*d3B/dx3
Date | Version | Created/Edited By | Description
2024-03-29 | 0 | Pedro | Firs draft based on data in the DDR, measured data of existing magnets and the most recent design studies by Alexey
2024-03-31 | 0.1 | Pedro | Updates of octupoles and sextupoles
2024-04-07 | 0.2 | Pedro | Updated description of limits for gradients in dipole magnets
2024-05-28 | 1 | Pedro | Complete reorganization with one tab per magnet type and new numbers from Alexey. Added sextupole trim coil limits (in quad mode)
2024-05-29 | 1.1 | Pedro | Corrected labelling of dipole magnet gradient limits. Introduced columns with central gradients calculated based on the lattice length of the magnets for QF-QFm, Qfend-Qdend
2024-05-30 | 1.2 | Alexey | Updated values for SFI-SFO and SDend @100A and 130 A -3D model
2024-06-01 | 1.3 | Pedro | Updated dip/dipm tables based on the assumption that a modified poleface design can provide both an increase or decrease of the gradient. Update of challenge level scale
2024-06-02 | 1.4 | Pedro | Formatting and further review of the challenege levels
2024-06-08 | 1.5 | Pedro | Formattin only, no changes to numbers
2024-06-11 | 1.6 | Alexey | Updated values for SFm and SD @100A and 130 A -3D model
2024-07-23 | 1.7 | Alexey | Updated values for OXX-OXY @ full current
2024-11-03 | 1.8 | Pedro | Added lines to QF-Qfm tab corresponding to increased magnet length. Updated Qf/QFm table based on Alexeys slides at the magnet review meeting. Added tab for reverse bend limits (WIP)
2024-11-05 | 1.9 | Pedro | Added tabs to indicate limits for the integrated dipole component in dipm and dip. Changed order of the tabs to correspond to the order in the LatticeSummaries table. Updated limits to reverse bends
2024-11-07 | 2 | Pedro | Updates to sextupole limits based on meeting held on 2024/11/06
2024-11-10 | 2.1 | Pedro | minor correction of labelling in the dip_field tab
2024-11-17 | 2.2 | Pedro | added tabs for ccombined function Sextupole/Quadrupoles
2024-11-25 | 2.3 | Pedro | added new range for OXX/OXY octupoles
2024-11-26 | 2.4 | Pedro | updated octupole tabs
2024-11-28 | 2.5 | Pedro | Updates notes on current status of Octupole power supplies
2024-12-02 | 2.6 | Pedro | Updates of octupole limits. Divisde the octupoles into three separate dabs
2024-12-07 | 2.7 | Pedro | Updates to octupole limits. Take into account that all octupole families have at least two magnets with larger bore diameter (36 mm) even if most have a smaller one (25 mm).
2025-01-26 | 2.8 | Pedro | Updates to Octupole limits, following latest calculations by Alexey and estimates by Åke of reduced aperture octupoles in achromat 1
2025-01-29 | 2.9 | Pedro | Updates to Octupole limits
2025-02-11 | 3 | Pedro | Updates to dipole magnet limits
2025-02-20 | 3.1 | Pedro | Updates to quadrupole components in sextupoles. Still Work In Progress, this is an updated guess based on more recent calculations
2025-02-23 | 3.2 | Pedro | Added the magnet tye (X1) , an extra 5-cm long quadrupole to be installed rght downstream of the U1 and U2 blocks and right upsteam of the U4 and u5 blocks.
2025-03-08 | 3.3 | Pedro | Added coupled combined funcion sextupoles/quadrupoles

## dipm_field
| Nominal Integrated Field | 0.26198 | T.m |  |  | Calculations were done for the unit cell dipole
| Coil current to achiev nominal deflection | 393 | A |  |  | Here we assumeno saturationm as was the case for the dip magnets
Magnet Type (DDR naming convention) | Design Features | Integrated Field [T] |  | Challenge Level | Comments
|  | Min | Max
dipm | as built | 0 | 0.26198 | 1
| as built plus existing power supply at maximum current | 0 | 0.29998 | 2

## dipm_gradient
| Nominal Integrated gradient | 4.2101 | T |  |  |  | Calculations were done for the unit cell dipole
| Nominal Strongest slice | 8.7266 | T/m |  |  |  | Here we assme the same factors for the matching cell dipole
Magnet Type (DDR naming convention) | Design Features | Gradient (strongest slice) [T/m] |  | Integrated Gradient [T] |  | Challenge Level | Comments | Min K [m**-2] | K [m**-2]
|  | Min | Max | Min | Max
dipm | as built | 8.3776 | 9.0757 | 4.0417 | 4.3785 | 1 | 4% range of existing pole face strips | 0.83703 | 0.90679
| as built plus extended range of pole face strip ps | 7.854 | 9.5993 | 3.7891 | 4.6311 | 2 | 10% range of pole face strips by increasing ps curent | 0.78472 | 0.9591
| Modified pole tip + existing range of pole face strips | -0.34906 | 11.373 | -0.1684 | 5.4868 | 10 | Maximum is based on 2D calculation (for the unit cell dipole) with modified pole face angle that allows an increase of the gradient by +/- 26.3 %. Minimum assumes new pole faces are parallel and the same absolute raneg is given by the pole face strips | -0.034876 | 1.1363
| Modified pole tip +extended range of pole face strips | -0.87266 | 11.8966 | -0.42101 | 5.7394 | 11 |  | -0.087191 | 1.1886

## dip_field
| Nominal Integrated Field | 0.52396 | T.m |  | Opera 3D excitation curve shows no sign of saturation up to 1.1 kA
| Coil current to achiev nominal deflection | 662.1818 | A
Magnet Type (DDR naming convention) | Design Features | Integrated Field [T.m] |  | Challenge Level | Comments
|  | Min | Max
dip | as built | 0 | 0.52396 | 1
| as built plus existing power supply at maximum current (750 A) | 0 | 0.60136 | 2
| as built + new power supply (1000 A) | 0 | 0.78387 | 3

## dip_gradient
| Nominal Integrated gradient | 8.5367 | T
| Nominal Strongest slice | 8.6666 | T/m
Magnet Type (DDR naming convention) | Design Features | Gradient (strongest slice) [T/m] |  | Integrated Gradient [T] |  | Challenge Level | Comments | Min K [m**-2] | K [m**-2]
|  | Min | Max | Min | Max
dip | as built | 8.3199 | 9.0132 | 8.1953 | 8.8782 | 1 | 4% range of existing pole face strips | 0.83128 | 0.90055
| as built plus extended range of pole face strip ps | 7.7999 | 9.5332 | 7.6831 | 9.3904 | 2 | 10% range of pole face strips by increasing ps curent | 0.77932 | 0.9525
| Modified pole tip + existing range of pole face strips | -0.34666 | 11.2948 | -0.34147 | 11.1256 | 10 | Bsaed on 2D calculation that allows a change of the gradient by +/- 26.3 % | -0.034636 | 1.1285
| Modified pole tip +extended range of pole face strips | -0.86666 | 11.8148 | -0.85367 | 11.6378 | 11 |  | -0.086591 | 1.1805
|  |  |  | 8.1953 | 8.8782
|  |  |  | 7.6831 | 9.3904
|  |  |  | -0.34147 | 11.1256
|  |  |  | -0.85367 | 11.6378

## QFend-Qdend
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Lattice Central Gradient [T/m] | Max Lattice Central Gradient [T/m] | Min Lattice Central K [m**-2] | Max Lattice Central K [m**-2]
|  |  |  | Min | Max |  |  | Qfend/Qdend - similar to QF/QFM (pole root width, profile, coil NW), but by 100 mm longer (yoke)=> Qfend=QF values(Lmag=144 mm) +100 mm
Qfend/Qdend | 0.25 | 0.244 | as built, measured @ nominal current (65 A) | 0 | 8.8 | 36.0656 | 1 |  | 0 | 35.2 | 0 | 3.517
|  |  | as built, measured @ higher current (77 A) | 0 | 9.61 | 39.3852 | 1 |  | 0 | 38.44 | 0 | 3.8407
|  |  | as built, max current (100 A) from existing ps , mag efficiency 76% | 0 | 11.5511 | 47.3408 | 1 |  | 0 | 46.2046 | 0 | 4.6165
|  |  | as built, upgraded ps (150 A), mag. efficiency 55.7 % | 0 | 12.7162 | 52.1154 | 2 |  | 0 | 50.8646 | 0 | 5.0821
|  |  | narrower poles + new pole material with existing ps at full current (100 A) | 0 | 13.462 | 55.1722 | 3 |  | 0 | 53.8481 | 0 | 5.3802
|  |  | narrower poles + new pole material, upgraded ps (150 A) | 0 | 15.0756 | 61.785 | 4 |  | 0 | 60.3022 | 0 | 6.025
|  |  | narrower poles + new pole material + thicker pole roots + new ps(148 A) | 0 | 16.1821 | 66.32 | 10 |  | 0 | 64.7283 | 0 | 6.4672

## QF-QFm
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Lattice Central Gradient [T/m] | Max Lattice Central Gradient [T/m] | Min Lattice Central K [m**-2] | Max Lattice Central K [m**-2]
|  |  |  | Min | Max
QF/QFm | 0.15 | 0.144 | as built, measured @ nominal curent (77.2 A) | 0 | 6.1836 | 42.9417 | 1 |  | 0 | 41.224 | 0 | 4.1188
|  |  | as built, measured @ higher current (85 A) , magnet efficiency at 84% | 0 | 6.4341 | 44.6814 | 1 |  | 0 | 42.8941 | 0 | 4.2857
|  |  | as built, max current (100 A) from existing ps , mag efficiency 76% | 0 | 6.8171 | 47.3408 | 1 |  | 0 | 45.4471 | 0 | 4.5408
|  |  | as built, upgraded ps (150 A), mag. efficiency 55.7 % | 0 | 7.5046 | 52.1154 | 2 |  | 0 | 50.0308 | 0 | 4.9988
|  |  | narrower poles + new pole material with existing ps at full current (100 A) | 0 | 7.9448 | 55.1722 | 3 |  | 0 | 52.9653 | 0 | 5.292
|  |  | narrower poles + new pole material, upgraded ps (150 A) | 0 | 8.897 | 61.785 | 4 |  | 0 | 59.3136 | 0 | 5.9263
|  |  | narrower poles + new pole material + thicker pole roots + new ps (110 A) | 0 | 9.5501 | 66.32 | 10 |  | 0 | 63.6672 | 0 | 6.3612
|  |  | narrower poles + new pole material + thicker pole roots + new ps (110 A) + magnet length increased by 60 mm | 0 | 13.5293 | 93.9533 | 11 | Space available in U2 and U3 blocks (QF magnets ), not in U1 (Qfm magnets). Valie estimated from scaling with length | 0 | 90.1951

## Xq
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Lattice Central Gradient [T/m] | Max Lattice Central Gradient [T/m] | Min Lattice Central K [m**-2] | Max Lattice Central K [m**-2]
|  |  |  | Min | Max
Xq (new magnet) | 0.05 | 0.05 | based o the maxium we can get from a Qfm with the present design quad, scaled by the length | 0 | 2.0612 | 41.224 | 1 |  | 0 | 41.224 | 0 | 4.1188
|  |  | based o the maxium we can get from a Qfm with thicker pole roots, scaled by the length | 0 | 3.1834 | 63.6672 | 2 |  | 0 | 63.6672 | 0 | 6.3612

## ReverseBend
Based on QF, bore diameter increased from 25 mm to 34 mm
Magnet Type (derived from the QF/QFm but with larger aperture | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Lattice Central Gradient [T/m] | Max Lattice Central Gradient [T/m] | Min Lattice Central K [m**-2] | Max Lattice Central K [m**-2]
|  |  |  | Min | Max
Rn | 0.15 | 0.144 | as built, measured @ nominal curent (77.2 A) | 0 | 3.3432 | 23.2167 | 1 | Based on scaling with the square of the bore radius | 0 | 22.2881 | 0 | 2.2269
|  |  | as built, measured @ higher current (85 A) , magnet efficiency at 84% | 0 | 3.4787 | 24.1573 | 1 |  | 0 | 23.191 | 0 | 2.3171
|  |  | as built, max current (100 A) from existing ps , mag efficiency 76% | 0 | 3.6857 | 25.5951 | 1 |  | 0 | 24.5713 | 0 | 2.455
|  |  | as built, upgraded ps (150 A), mag. efficiency 55.7 % | 0 | 4.0574 | 28.1766 | 2 |  | 0 | 27.0495 | 0 | 2.7026
|  |  | narrower poles + new pole material with existing ps at full current (100 A) | 0 | 4.2954 | 29.8293 | 3 |  | 0 | 28.6361 | 0 | 2.8611
|  |  | narrower poles + new pole material, upgraded ps (150 A) | 0 | 4.8103 | 33.4045 | 4 |  | 0 | 32.0684 | 0 | 3.2041
|  |  | narrower poles + new pole material + thicker pole roots + new ps (148 A) | 0 | 7 | 48.6111 | 10 | from Alexey´s presentation at magnet review | 0 | 46.6667 | 0 | 4.6626
|  |  | narrower poles + new pole material + thicker pole roots + new ps (148 A) + magnet length increased by 60 mm | 0 | 10 | 69.4444 | 11 | from Alexey´s presentation at magnet review | 0 | 66.6667

## Sdend
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T/m] |  | Max Central Gradient [T/m**2] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**2] | Max Lattice Central Gradient [T/m**2] | Min Lattice Central K [m**-3] | Max Lattice Central K [m**-3]
|  |  |  | Min | Max
Sdend | 0.1 | 0.1026 | as built, measured @ nominal current (69.9 A) | 0 | 173.707 | 1693.0507 | 1 |  | 0 | 1737.07 | 0 | 173.5573
|  |  | as built, measured @ higher current (82 A) | 0 | 192.03 | 1871.6374 | 1 |  | 0 | 1920.3 | 0 | 191.8645
|  |  | as built, highest current with existing ps (100 A) | 0 | 210.604 | 2052.6706 | 1 | OPERA 3D model 30.05.2024 | 0 | 2106.04 | 0 | 210.4225
|  |  | as built, upgraded power supply (130 A) | 0 | 232.004 | 2261.2476 | 2 | OPERA 3D model 30.05.2024 | 0 | 2320.04 | 0 | 231.804
|  |  | Same as existing magnet + 18 mm longer towards downstream end in M1 and upstream end in M2, 130 A | 0 | 272.7065 | 2657.9577 | 3 | To be calculated, present value obtained scaling with the length | 0 | 2727.0646 | 0 | 272.4714
|  |  | conical shaped poles + increase the width of the pole at the root , and return yoke, reduced the pole tip, existing power suppy (100 A) + 18 mm longer as above. | 0 | 313.6124 | 3056.6513 | 4 | To be calculated , the present vaue is s wild guess (15%) | 0 | 3136.1242 | 0 | 313.3421
|  | Measured values (average all Magnets SDend) |  |  |  | OPERA 3D model
|  | Imain(A) | B"/2·L (T/m) |  |  | Imain(A), Itrim=0A | B"/2·L(T/m)
|  | 0 | 1.3205 |  |  | 0 | 0
|  | 18.6387 | 48.828 |  |  | 56 | 142.5324
|  | 37.2866 | 96.0429 |  |  | 70 | 175.3176
|  | 55.938 | 142.4748 |  |  | 74.6 | 183.0332
|  | 74.5849 | 182.0758 |  |  | 82 | 192.6122
|  | 82.0462 | 192.0789 |  |  | 90 | 201.322
[6 empty] | 100 | 210.604
[6 empty] | 110 | 218.582
[6 empty] | 130 | 232.004

## Sfm
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T/m] |  | Max Central Gradient [T/m**2] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**2] | Max Lattice Central Gradient [T/m**2] | Min Lattice Central K [m**-3] | Max Lattice Central K [m**-3]
|  |  |  | Min | Max
Sfm except special (11 turns/coil Inom=~83 A ): R3-302U1/MAG/SXFM-01 R3-302U5/MAG/SXFM-01 | 0.1 | 0.103 | as built, measured @ nominal current (69.9 A) | 0 | 171.547 | 1665.5049 | 1 |  | 0 | 1715.47 | 0 | 171.3991
|  |  | as built, measured @ higher current (82 A) | 0 | 190.175 | 1846.3592 | 1 |  | 0 | 1901.75 | 0 | 190.0111
|  |  | as built, highest current with existing ps (100 A) | 0 | 208.732 | 2026.5243 | 1 | OPERA 3D model 11.06.2024 | 0 | 2087.32 | 0 | 208.5521
|  |  | as built, upgraded power supply (130 A) | 0 | 224.534 | 2179.9417 | 2 | OPERA 3D model 11.06.2024 | 0 | 2245.34 | 0 | 224.3405
|  |  | same as exisrting magnet , 10 mm longer | 0 | 246.3334 | 2391.5866 | 3 | To be calculated, present value obtained scaling with the length | 0 | 2463.3342 | 0 | 246.1211
|  |  | narrower poles+remove cutouts | 0 | 316 | 3067.9612 | 4 | From calculations by LJL | 0
|  |  | narrower poles+remove cutouts + 10 mm longer @ 130 A | 0 | 347.6 | 3374.7573 | 5 | same as abovce scaled by length |  | 3476
narrower poles + remove cutouts
10 mm longer
[8 empty] | make poles narrower and even lomger magnet | whatwas this ?

## Sd
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T/m] |  | Max Central Gradient [T/m**2] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**2] | Max Lattice Central Gradient [T/m**2] | Min Lattice Central K [m**-3] | Max Lattice Central K [m**-3]
|  |  |  | Min | Max
Sd | 0.1 | 0.102 | as built, nominal current ( 55.9 A) | 0 | 117.782 | 1154.7255 | 1 | j@130A=12 A/mm2, cooling OK: ΔT=6.5°C @ΔP=2 bar | 0 | 1177.82 | 0 | 117.6805
|  |  | as built, measured @ higher current ( 66.4 A) | 0 | 138.884 | 1361.6078 | 1 |  | 0 | 1388.84 | 0 | 138.7643
|  |  | as built, highest current with existing ps ( 100 A) | 0 | 192.1706 | 1884.0255 | 1 | OPERA 3D model 11.06.2024 | 0 | 1921.706 | 0 | 192.005
|  |  | as built, upgraded power supply (130 A) | 0 | 213.214 | 2090.3333 | 2 | OPERA 3D model 11.06.2024 | 0 | 2132.14 | 0 | 213.0302
|  |  | as exisitng magnet but 35 mm (25 mm upstream, 10mm downstream for the SD upstream of dipole) @ 130 A | 0 | 275.924 | 2705.1373 | 3 | To be calculated, present value obtained scaling with the length | 0 | 2759.24 | 0 | 275.6862
|  |  | increase pole width, change coils within the outer envolope + 35 mm longer | 0 | 459.216 | 4502.1176 | 4 | Based on Henriques 2D calculations plus scaling with length | 0 | 4592.16 | 0 | 458.8202
|  |  | increase pole width, change coils within the outer envolope + 80 mm longer (requirs new block) | 0 | 606.9522 | 5950.5113 | 10 | Based on Henriques 2D calculations plus scaling with length | 0 | 6069.5216 | 0 | 606.429

## SFI-SFO
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T/m] |  | Max Central Gradient [T/m**2] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**2] | Max Lattice Central Gradient [T/m**2] | Min Lattice Central K [m**-3] | Max Lattice Central K [m**-3]
|  |  |  | Min | Max
SFI/SFO | 0.1 | 0.1034 | as built, nominal current (77.3 A) | 0 | 210.4 | 2034.8162 | 1 |  | 0 | 2104 | 0 | 210.2186
|  |  | as built, measured @ higher current (86.4 A) | 0 | 220.7 | 2134.4294 | 1 |  | 0 | 2207 | 0 | 220.5098
|  |  | as built, highest current with existing ps (100 A) | 0 | 236.916 | 2291.2573 | 1 | OPERA 3D model 30.05.2024 | 0 | 2369.16 | 0 | 236.7118
|  |  | as built, upgraded power supply (130 A) | 0 | 258.308 | 2498.1431 | 2 | OPERA 3D model 30.05.2024 | 0 | 2583.08 | 0 | 258.0853
|  |  | as the existing magnet, longer by 10 mm (upstream for the U1 block) @ 130 A | 0 | 283.2894 | 2739.743 | 3 | To be calculated, present value obtained scaling with the length | 0 | 2832.8943 | 0 | 283.0452
|  |  | Narrower pole + longer maget by 10 mm @ 130 A | 0 | 325.7828 | 3150.7045 | 4 | To be calculated, present number is a wild guess (15%) | 0 | 3257.8285 | 0 | 325.502
|  | Measured values (average all Magnets Sfi and SFo) |  |  |  | OPERA 3D model
|  | Imain(A) | B"/2·L (T/m) |  |  | Imain(A), Itrim=0A | B"/2·L(T/m)
|  | 0 | 0.90856 |  |  | 0 | 0
|  | 16.5447 | 48.1477 |  |  | 66.2 | 191.8032
|  | 19.6285 | 58.2893 |  |  | 72.8 | 205.064
|  | 33.0987 | 95.4023 |  |  | 78.6 | 213.672
|  | 39.2702 | 115.2194 |  |  | 86.4 | 223.296
|  | 49.6553 | 142.3055 |  |  | 100 | 236.916
|  | 58.9084 | 171.2037 |  |  | 110 | 245.088
|  | 66.2162 | 187.0938 |  |  | 130 | 258.308
|  | 72.8386 | 200.1782
|  | 78.5493 | 211.6853
|  | 86.4021 | 220.6711

## OXX
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T.m**2] |  | Max Central Gradient [T/m**3] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**3] | Max Lattice Central Gradient [T/m**3] | Min Lattice Central K [m**-4] | Max Lattice Central K [m**-4]
|  |  |  | Min | Max
OXX | 0.1 | 0.1008 | as built | 0 | 3486.6639 | 34589.9192 | 1 | 25 mm aperture - for all achromats except achromat 1, ps at 56.88 A 36 mm aperture for achromat 01 , ps at 247 A | 0 | 34866.6386 | 0 | 3483.6584
|  |  | new ps for all achromats except 01 | 0 | 5601.7808 | 55573.2225 | 2 | 25 mm aperture - for all achromats except achromat 1, ps at 91 A 36 mm aperture for achromat 01 , ps at 400 A | 0 | 56017.8083 | 0 | 5596.9522
|  |  | new ps all achromats | 0 | 6595.8551 | 65435.0705 | 3 | 25 mm aperture - for all achromts except achromat 1, ps at 107 A 36 mm aperture for achromat 01 , ps at ~500 A | 0 | 65958.5511 | 0 | 6590.1696
|  |  | new ps all achromats + new octupoles with 34 mm bore diamter in achromat 01 (estimate by Åke) | 0 | 8244.8189 | 81793.8382 | 4 | 25 mm aperture - for all achromts except achromat 1, ps at 134 A 34 mm aperture for achromat 01 , ps at ~500 A . To be confirmed | 0 | 82448.1889 | 0 | 8237.712
Notes | 38 of the OXXs are today fed by one power supply ( R3_A102011CAB19_MAG_PSPH01) |  |  |  | This is a delta model SM-60.100 with max ratings 100 A/60 V. In routine operation we have 28.3 A/29.85 V |  |  |  | max current limited by voltage |  | 56.8844 | A
| 2 of the OXXs (in achromat 1) are fed from R3_A110111CAB08_MAG_PSPE01; This is a Delta SM-15 400 with max ratings 400 A/15 V, In routine operation we have 41.4 A /1 0 V | [7 empty] | max current limited by volatge |  | 621 | A

## OXY
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T.m**2] |  | Max Central Gradient [T/m**3] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**3] | Max Lattice Central Gradient [T/m**3] | Min Lattice Central K [m**-4] | Max Lattice Central K [m**-4]
|  |  |  | Min | Max
OXY | 0.1 | 0.1008 | as built | 0 | 6595.856 | 65435.0794 | 1 | 25 mm aperture - for all achromats except achromat 1, ps at 107 A 36 mm aperture for achromat 01 , ps at 500 A | 0 | 65958.56 | 0 | 6590.1705
|  |  | new ps all achromats + new octupoles with 34 mm bore diamter in achromat 01 (estimate by Åke) | 0 | 8244.82 | 81793.8492 | 2 | 25 mm aperture - for all achromats except achromat 1, ps at 134 A 36 mm aperture for achromat 01 , ps at 500 A | 0 | 82448.2 | 0 | 8237.7132
Notes | 38 of the OXYs are today fed from R3_A102011CAB16_MAG_PSDA01. This is a Danfysik 859-1Q 175A/100V . In routin e operation we have 57.3 A/49.6 V | [7 empty] | max current limited by voltage |  | 115.5242 | A
| 2 of the OXYs (in achromat 1) are fed by R3_A102011CAB18_MAG_PSDG01. This is a Danfysilk 859-1Q 500A/22V. In routine operation we have 254 A/8V | [7 empty] | max current limited by voltage |  | 698.5 | A
133.75

## OYY
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T.m**2] |  | Max Central Gradient [T/m**3] | Challenge Level | Comments | Min Lattice Central Gradient [T/m**3] | Max Lattice Central Gradient [T/m**3] | Min Lattice Central K [m**-4] | Max Lattice Central K [m**-4]
|  |  |  | Min | Max
OYY | 0.1 | 0.1 | as built at 179 A | 0 | 2530.1139 | 25301.1389 | 1 | maximum volatge of existing power supply | 0 | 25301.1389 | 0 | 2527.933
|  |  | as built + new power supply at 500 A | 0 | 6595.856 | 65958.56 | 2 | new power supply | 0 | 65958.56 | 0 | 6590.1705
|  |  | new octupoles with 34 mm bore radius + new power supply | 0 | 8244.82 | 82448.2 | 3 | new power supply and new magnets | 0 | 82448.2 | 0 | 8237.7132
Notes | All 40 OYY magnets are today fed in series by R3_A102011CAB17_MAG_PSDB01. This is a Danfysik 859-1Q 225A/110V. In routine operation we have today 94.9 A/58.3 V | [7 empty] | maximum current limited by voltage |  | 179.0566 | A
0.61433
|  |  | 12.5 mm |  |  |  |  | 138.2244

## SextTrimsQ
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Int K [m**-1] | Max Int K [m**-1]
|  |  |  | Min | Max
SextTrimsQ | 0.1 | 0.1 | as built, measured @ max current (5 A) | 0 | 0.1 | 1 | 1 | From email from Alexey on 2024/05/21. updated guestimate based on calculations February 2025 | 0 | 0.0099914
|  |  | new coil design and power supplies | 0 | 0.29 | 2.9 | 2 |  | 0 | 0.028975

## Sdend_CombQ
Quadrupole component in sextupole magnet Sdend
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Int K [m**-1] | Max Int K [m**-1]
|  |  |  | Min | Max
Sdend_combQ | 0.1 | 0.1 | as built, measured @ max current (5 A) | 0 | 0.1 | 1 | 1 | merely a copy from the trim coil tab | 0 | 0.0099914
|  |  | new coil design and power supplies | 0 | 0.29 | 2.9 | 2 | merely a copy from the trim coil tab | 0 | 0.028975

## Sd_CombQ
Quadrupole component in sextupole magnet Sdend
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Gradient [T] |  | Max Central Gradient [T/m] | Challenge Level | Comments | Min Int K [m**-1] | Max Int K [m**-1]
|  |  |  | Min | Max
Sd_combQ | 0.1 | 0.1 | as built.redistribution of total NI | 0 | 0.1 | 0.1 | 1 | guesstimate | 0 | 0.0099914
|  |  | new coil design and power supplies | 0 | 0.15 | 0.15 | 2 | guesstimate | 0 | 0.014987

## Sd_Comb_Coupled
Quadrupole component in sextupole magnet Sdend
Magnet Type (DDR naming convention) | Lattice Length [m] | Magnetic Length [m] | Design Features | Integrated Sextupol Gradient [T/m] |  | Integrated Quadrupole Gradient [T] |  | Challenge Level | Comments
|  |  |  | Min | Max | Min | Max
Sd_combQ | 0.1 | 0.1 | as built | 139.9 | 240.2 | 0 | 0.898 | 1 | From Henrique´s c2D calcualations
|  |  | new poles | 221.3 | 340.16 | 0 | 0.82 | 2 | From Henrique´s c2D calculations

## Ver. 0.0 1st Draft
Magnet Type (DDR naming convention) | Lattice Length [m] | Design Features | Max integrated gradient |  | Max Gradient
QF/QFm | 0.15 | as built, measured @ nominal curent (77.2 A) | 6.1836 | T | 41.224 | T/m
|  | as built, measured @ higher current (85 A) , magnet efficiency at 84% | 6.4341 | T | 42.8941 | T/m
|  | as built, max current (100 A) from existing ps , mag efficiency 76% | 6.8171 | T | 45.4471 | T/m
|  | as built, upgraded ps (150 A), mag. efficiency 55.7 % | 7.5046 | T | 50.0308 | T/m
|  | narrower poles + new pole material with existing ps at full current (100 A) | 7.9448 | T | 52.9653 | T/m
|  | narrower poles + new pole material, upgraded ps (150 A) | 8.897 | T | 59.3136 | T/m
|  | narrower poles + new pole material + thicker pole roots + new ps(148 A) | 9.5501 | T | 63.6672 | T/m
Qfend/Qdend | 0.25 | as built, measured @ nominal current (65 A) | 9.1746 | T | 36.6985 | T/m
|  | as built, @ max current from existing ps (100 A) | 15.291 | T | 61.1642 | T/m | Obs: to be checked - for now just simple scaling
Sdend | 0.1 | as built, measured @ nominal current (69.9 A) | 170.755 | T.m | 1707.55 | T/m**2
|  | as built, measured @ higher current (82 A) | 200.08 | T.m | 2000.8 | T/m**2
|  | as built, highest current with existing ps (100 A) | 244 | T.m | 2440 | T/m**2 | Obs: to be checked - for now just simple scaling
|  | as built, upgraded power supply (130 A) | 317.2 | T.m | 3172 | T/m**2 | Obs: to be checked - for now just simple scaling
Sfm/Sfo | 0.1 | as built, nominal current (70.1 A) | 170.193 | T.m | 1701.93 | T/m**2
|  | as built, measured @ higher current (82 A) | 212.0594 | T.m | 2120.5938 | T/m**2
|  | as built, highest current with existing ps (100 A) | 258.609 | T.m | 2586.09 | T/m**2 | Obs: to be checked - for now just simple scaling
|  | as built, upgraded power supply (130 A) | 336.1917 | T.m | 3361.917 | T/m**2 | Obs: to be checked - for now just simple scaling
Sd | 0.1 | as built, nominal current ( 55.9 A) | 117.782 | T.m | 1177.82 | T/m**2
|  | as built, measured @ higher current ( 66.6 A) | 140 | T.m | 1400 | T/m**2
|  | as built, highest current with existing ps ( 100 A) | 210.2102 | T.m | 2102.1021 | T/m**2 | Obs: to be checked - for now just simple scaling
|  | as built, upgraded power supply (130 A) | 221.9512 | T.m | 2219.5122 | T/m**2 | Obs: to be checked - for now just simple scaling
Sfi | 0.1 | as built, nominal current (77.3 A) | 210.4 | T.m | 2104 | T/m**2
|  | as built, measured @ higher current (86.4 A) | 235.008 | T.m | 2350.08 | T/m**2
|  | as built, highest current with existing ps (100 A) | 272 | T.m | 2720 | T/m**2 | Obs: to be checked - for now just simple scaling
|  | as built, upgraded power supply (130 A) | 372.5737 | T.m | 3725.7366 | T/m**2 | Obs: to be checked - for now just simple scaling
OXX, OXY | 0.1 | as built, measured @ nominal current (106.7 A) | 6589.73 | T.m**2 | 65897.3 | T/m**3
|  | as built at highest current from existing ps | 6589.73 | T.m**2 | 65897.3 | T/m**3 | Obs: to be checked - for now just duplicate at lower current
OYY | 0.1 | as built, nominal current (203.901 A) | 2850.71 | T.m**2 | 28507.1 | T/m**3
|  | as built at highest current from existing ps | 2850.71 | T.m**2 | 28507.1 | T/m**3 | Obs: to be checked - for now just duplicate at lower current
dipm |  | as built |  |  | 8.7266 | T/m
|  | Gradient adjustment range with existing pole face strips and ps |  |  | 4 | % | Obs: to be checked
|  | Gradient adjustment range with modified pole face strip + new ps ?? |  |  | 10 | % | Obs: to be checked
as built, existing poleface strips
|  | Minimum gradient |  |  | 8.3776 | T/m
|  | Maximum gradient |  |  | 9.0757 | T/m
as built, modified poleface strips
|  | Minimum gradient |  |  | 7.854 | T/m
|  | Maximum gradient |  |  | 9.5993 | T/m
|  | modified pole tip (2D modelling) - no poleface strips |  |  | 10.95 | T/m | Obs: to be checked - for now just assume same as dip
|  | Minimum gradient (modified pfs) |  |  | 9.855 | T/m
|  | Maximum gradient (modified pfs) |  |  | 12.045 | T/m
dip |  | as built |  |  | 8.6681 | T/m
|  | Gradient adjustment range with existing pole face strips and ps |  |  | 4 | %
|  | Gradient adjustment range with modified pole face strip + new ps ?? |  |  | 10 | % | Obs: to be checked - for now just assume 10%
as built, existing poleface strips
|  | Minimum gradient |  |  | 8.3213 | T/m
|  | Maximum gradient |  |  | 9.0148 | T/m
as built, modified poleface strips
|  | Minimum gradient |  |  | 7.8013 | T/m
|  | Maximum gradient |  |  | 9.5349 | T/m
|  | modified pole tip (2D modelling) |  |  | 10.95 | T/m
|  | Minimum gradient (modified pfs) |  |  | 9.855 | T/m
|  | Maximum gradient (modified pfs) |  |  | 12.045 | T/m